## Sprint1
Title | Description
> Set up the MongoDB collection for the steam game library | 30 min
> Seed the SteamGame data into the DB Collection | 1 hr
> Create node.js server | 10 min
> Create eslint config | 15 min
> Create a route called /steamgames/ that fetches all the games from the DB | 1 hr
> Create a route called /steamgames/<gameid> that fethces the specific game information from DB | 1 hr
> Display then list of games in a list on main page | 15 min
> Setup unit tests for the 2 working endpoints | 1hr
> Setup unit test for seeding | 1hr
> Add test job | 15 min
> Add eslint job | 15 min
> Add build job with an accompanying artifact | 30 min
> Cache image to local storage | 1 hr
> Setup fetching images from steam api and display them on page | 2 hr
> Scrolling horizontally to display the 200 games looped through | 2 hr
> Design the basic layout and CSS for the react app main page | 3 hr
> Searching for a game by string matches the search/letters | 1 hr
> Search field at the top left | 15 min
> Searching for a game dynamically adjusts the images displayed | 3 hrs
> Able to search for games by other fields (developer, year published) | 2 hr
As a user, I want to see a detailed page of a steam game i select
> Fetch the individual game image | 1 hr
> Display the game title, description and dev info on the page | 6 hr
> Add nav route to navigate image to the game with populated info from steam api | 1hr
> Hover on image to show confirmation of user interaction | 1hr
> Setup a common steam account with a shared api key | 30 min
> To avoid more responses than unnecessary, we cache the responses. | 1 hr
> Look over docs for OAuth integration with steam | -
> Retrieve API key | -
> Lookup validating if the service is down, to ensure you can login with account credentials instead | -
> Register through the OAuth | -
> Successful linked account will have the images links | -
> Get linked usernames associated with the steam account | -

## Sprint2
Steam account will create a user account using 0Auth

## Sprint3
Sprint 3
User list contains a list of all the games in the api